## Slide 1: FIP Semi-Annual Report
DATE June 16, 2016
PLACE Oaxaca, Mexico
VENUE Meeting of the FIP Sub-Committee

## Slide 2: Strategic Issues
Global interest in forests with Paris Agreement, INDCs, SDGs
Challenge of how these can be implemented and role for FIP
New chapter for FIP: working with 8 original, 6 new and 9 additional FIP countries
Resource availability within FIP
Portfolio trends and disbursements
DGM progress

## Slide 3: FIP Pilot Countries
FIP at important point in its development
  8 Pilot Countries IPs approved, under implementation
  6 New Pilot Countries, IPs under development
  9 Additional Countries, IPs under development (without investment funds)
Evolving architecture with Paris Agreement, INDCs and SDGs, and GCF

## Slide 4: New and Additional Country Updates
Country | MDBs | Dialogue | Scoping Mission | Joint Mission | Notes
Congo Rep | AfDB, IBRD |  |  |  | 
Cote d’Ivoire | AfDB, IBRD |  |  |  | IP submitted for SC
Ecuador | IDB, IBRD, IFC |  |  |  | 
Guatemala | IDB |  |  |  | 
Mozambique | AfDB, IBRD, IFC |  |  |  | IP submitted for SC
Nepal | IBRD |  |  |  | 
Bangladesh | ADB, IBRD, IFC |  |  |  | 
Cambodia | ADB |  |  |  | 
Cameroon | AfDB, IBRD |  |  |  | 
Guyana |  |  |  |  | 
Honduras | IDB, IBRD, IFC |  |  |  | Joint PPCR/FIP scoping mission
Rwanda | AfDB, IBRD |  |  |  | Joint PPCR/FIP scoping mission
Tunisia | AfDB, IBRD, EBRD |  |  |  | 
Uganda | AfDB, IBRD |  |  |  | Joint PPCR/FIP scoping mission
Zambia | AfDB, IBRD, IFC |  |  |  | 

## Slide 5: Resources Availablity
 | USD Million
Unrestricted Fund Balance | 343.7
Total Anticipated Commitments | 393.0
Available Resources (Balance – Commitments) | (49.3)
Potential Future Resources | 56.9
Potential Available Resources | 7.6
Addendum to update resource availability schedule and project approvals as of May 31, 2016, extract:

## Slide 6: FIP Overview
 | Endorsed Indicative Allocation |  |  |  | Approved funding |  | Disbursement
 | TOTAL | IP | DGM | PSSA | Committee | MBD | 
FIP Funding (in USD M) | 555.2 | 455.0 | 80.0 | 20.3 | 325.1 | 291.8 | 36.1
Number of projects | 47 | 27 | 16 | 4 | 22 | 18 | 14
FIP Portfolio (USD million)
At December 31, 2015
USD 555.2 has been endorsed by the FIP Sub-Committee
  8 endorsed Investment Plans
  DGM first and second tranches
  Private Sector Set Aside

## Slide 7: Trends in Funding Approvals by FY
Cumulative funding approvals have risen steadily
By December 31, 2015 59% of currently endorsed funding was approved by the Sub-Committee and 53% approved by MDBs
12 projects projected to be submitted for Sub-Committee approval by end of FY17
Pipeline tracking

## Slide 8: Co-financing
Projected co-financing for endorsed portfolio USD 970.5 million (ratio of 1:1.75)
Heavily influenced by Mexico FCCP with co-finance of USD 683 million
Portfolio co-finance without Mexico FCCP is USD 287.4 million (ratio of 1:0.56)
Main sources MDBs and Governments
Indicative FIP Co-Financing Breakdown by Source on Approved Projects a) with the Mexico project; and b) without the Mexico project

## Slide 9: Portfolio by Thematic Focus
46% of FIP funds focus on capacity building activities
Reflects long term position of sector in many countries
Foundational elements essential for lasting transformational change e.g. inter-ministerial dialogue, stakeholder engagement, policy and regulatory reform etc.

## Slide 10: Disbursements
Actual disbursements continue upward trend
Disbursement rates remain low totaling USD 36.1 million, 12% of MDB approved funding
Pattern reflects relative immaturity of program and rates expected to pick up as portfolio moves through project cycle

## Slide 11: Dedicated Grant Mechanism
$80 million allocated for 14 FIP countries and a Global Learning and Knowledge Exchange Project
Brazil and Peru DGM launched
Global DGM effective June 2015, first Global Steering Committee held in Bali July 2015, outreach events at Paris COP

## Slide 12: Gender and M&R in the FIP
Project performance on gender had improved
Review of three scorecard indicators
  Sector-specific analysis 67% (cf. SCF average 85%)
  Gender-disaggregated indicators 50% (cf. SCF average 71%)
  Women-specific activities 67% (cf. SCF average 77%)
M&R scoring workshops planned for Ghana, Brazil
GHG methodologies workshop 2016
FIP M&R Toolkit revised to include gender-disaggregated results for all relevant indicators